## Sheet1
| ID | Product Backlog | Priority | Effort | Status(Start - End)
Sprint 1 | 1 | A patient should be able to list institues showing price | 8 | 3 | Completed ¦¦ 28/01 - 30/01 | New points for the sprint backlog founded from sprint 2 for sprint 3: | Reason:
| 2 | A patient should be able to list institutions sorted by price of procedure | 8 | 3 | Completed ¦¦ 29/01 - 30/01
| 3 | A patient should be able to retrieve institutions address and zipcode | 8 | 3 | Completed ¦¦ 29/01 - 30/01
| 4 | A patient should be able to view map | 8 | 1 | Completed ¦¦ 30/01 - 31/01
| 5 | A patient should be able to select what procedure they want for institution list | 8 | 3 | Completed ¦¦ 29/01 - 30/01
Sprint 2 | 6 | A patient should be able to view institutions on map | 8 | 6 | Incomplete ¦¦
| 7 | A patient should be able to find institution based on distance Or Price | 8 | 4 | Incomplete ¦¦ | New points for the next sprint backlog after sprint meeting: | Reason:
| 8 | A Patient should be able to find institutes showing price and distance | 8 | 4 | Incomplete ¦¦
| 9 | A patient should be able to find institution by price based on procedures | 8 | 4 | Incomplete ¦¦
| 10 | A patient should be able to view institutions on map as well as price | 7 | 4 | Incomplete ¦¦
| 11 | A patient can track current location on map | 7 | 4 | Incomplete ¦¦
| 12 | A patient can input own location on map | 7 | 4 | Incomplete ¦¦ | Optional if we have time
| 13 | A Patient should be able to view his location on the map | 7 | 4 | Incomplete ¦¦ | A patient should be able to find institution based on custom ranking(price,distance, feedback)(Optional) | 2 | 6 | Incomplete ¦¦
| 14 | A Patient should be able to insert part of a procedure name in order to retrieve full procedure name | 7 | 3 | Incomplete ¦¦ | Dev should be able to manage data(Update, Add, Delete)(Optional) | 2 | 4 | Incomplete ¦¦
| 15 | A Patient should be able to find institution just based on procedures | 6 | 3 | Incomplete ¦¦ | Machine Learning based on patient selection(Optional) | 2 | 3 | Incomplete ¦¦
[6 empty] | A patient with disability should be able to work the site(Optional) | 2 | 5 | Incomplete ¦¦