## Sheet1
| Backlog | Status |  |  |  | Week 1(27/01/2020 - 31/01/2020) | [5 empty] | Comments
| Product | Priority[P] | Estimate[E] | Completed/Incompleted ¦¦ Sart:End | Assigned/Working on it | 03/02 - Monday | 04/02 - Tuesday | 05/02 - Wednesday | 06/02 - Thursday | 07/02 - Friday | 08/02 - Saturday
Sprint 2 | A patient should be able to view institutions on map | 8 | 6 | Completed ¦¦ 03/02 - 04/02 |  | 3=1+1+1 | 3=1+1+1
| A patient should be able to find institution based on distance Or Price | 8 | 4 | Completed ¦¦ 03/02 - 05/02 |  | 2=1+1 | 1=1 | 1=1
| A Patient should be able to find institutes showing price and distance | 8 | 4 | Incompleted ¦¦ 05/02 |  |  |  | 2=1+1
| A patient should be able to find institution by price based on procedures | 8 | 4 | Incompleted ¦¦ 04/02 |  |  | 2=1+1 | 1=1
| A patient should be able to view institutions on map as well as price | 7 | 4 | Incompleted ¦¦
| A patient can track current location on map | 7 | 4 | Completed ¦¦ 03/02 - 04/02 |  | 2=1+1 | 2=1+1
| A patient can input own location on map | 7 | 4 | Incompleted ¦¦ 05/02 |  |  |  | 2=1+1
| A Patient should be able to view his location on the map | 7 | 4 | Completed ¦¦ 04/02 - 05/02 |  |  | 2=1+1 | 2=1+1
| A Patient should be able to insert part of a procedure name in order to retrieve full procedure name | 7 | 3 | Completed ¦¦ 03/02 - 05/02 |  | 2=1+1 |  | 2=1+1
| A Patient should be able to find institution just based on procedures | 6 | 3 | Incompleted ¦¦
|  |  |  | Story Points Left | Day 0 | Day 1 | Day 2 | Day 3 | Day 4
[5 empty] | 40 | 31 | 21 | 11 | 11 |  | Note: Colour
Alif
Dillon
Ren
| New points for the sprint backlog founded from sprint 2 for sprint 3: | Reason: | [8 empty] | Costin
Jay
Justus