## Sheet1
| ID | Product Backlog | Priority | Effort | Status(Start - End)
Sprint 1 | 1 | Research Unit testing for PHP and how to implement | 10 | 6 | Completed ¦¦ 27/01 - 29/01 | New points for the sprint backlog founded from sprint 1 for sprint 2: | Reason:
| 2 | Research Map API to use and how to implement | 10 | 5 | Completed ¦¦ 27/01 - 29/01 | A patient should get a list of institutes from just procedures E:4 P:6 | QoL and ease of usage
| 3 | Set up Github with html Page View | 10 | 5 | Completed ¦¦ 27/01 - 28/01 | Research new API for maps E:2 P:6 | Old API usage needed server to run however unsure
| 4 | Research how to use Java servelet(Netbeans) | 10 | 1 | Completed ¦¦ 27/01 - 27/01 | Make sure that the elements on website changes with device E:1 P:2 | (QoL)Phones and laptops work however font is too big
| 5 | Research geocoding and how to utilise with API | 10 | 6 | Completed ¦¦ 29/01 - 30/01
| 6 | Research transfer of excel data into MYSQL workbench (database) | 10 | 2 | Completed ¦¦ 28/01 - 29/01
| 7 | Create/choose HTML backbone for project | 9 | 1 | Completed ¦¦ 27/01 - 27/01 | New points for the next sprint backlog after sprint meeting: | Reason:
| 8 | Secure a database and webspace(for hosting) for this project | 9 | 1 | Completed ¦¦ 28/01 - 28/01 | There should be a search bar that filters user input to show most likely procedure E:4 P:8 | QoL from sprint review
| 9 | Translate unique location in data set into geolocation(x & y) | 8 | 1 | Completed ¦¦ 29/01 - 29/01 | Take map off the front page and put it after a search has been made E:2 P:8 | Map has no use in front page
| 10 | A patient should be able to list institues showing price | 8 | 3 | Completed ¦¦ 28/01 - 30/01
| 11 | A patient should be able to list institutions sorted by price of procedure | 8 | 3 | Completed ¦¦ 29/01 - 30/01
| 12 | A patient should be able to retrieve institutions address and zipcode | 8 | 3 | Completed ¦¦ 29/01 - 30/01 | Optional if we have time
| 13 | A patient should be able to view map | 8 | 1 | Completed ¦¦ 30/01 - 31/01 | A patient should be able to find institution based on custom ranking(price,distance, feedback)(Optional) | 2 | 6 | Incomplete ¦¦
| 14 | A patient should be able to select what procedure they want for institution list | 8 | 3 | Completed ¦¦ 29/01 - 30/01 | Dev should be able to manage data(Update, Add, Delete)(Optional) | 2 | 4 | Incomplete ¦¦
Sprint 2 | 15 | A patient should be able to view institutions on map | 8 | 6 | Incomplete ¦¦ | Machine Learning based on patient selection(Optional) | 2 | 3 | Incomplete ¦¦
| 16 | A patient should be able to find institution based on distance/Price | 8 | 4 | Incomplete ¦¦ | A patient with disability should be able to work the site(Optional) | 2 | 5 | Incomplete ¦¦
| 17 | A Patient should be able to find institures showing price and distance | 8 | 4 | Incomplete ¦¦
| 18 | A patient should be able to find institution by price based on procedures | 8 | 4 | Incomplete ¦¦
| 19 | A patient should be able to view institutions on map as well as price | 7 | 4 | Incomplete ¦¦
| 20 | A patient can track current location on map | 7 | 4 | Incomplete ¦¦
| 21 | A patient can input own location on map | 7 | 2 | Incomplete ¦¦
| 22 | A Patient should be able to view his location on the map | 7 | 2 | Incomplete ¦¦