## Sheet1
| Backlog | Status |  |  |  | Week 1(27/01/2020 - 31/01/2020) | [5 empty] | Comments
| Product | Priority[P] | Estimate[E] | Completed/Incompleted ¦¦ Sart:End | Assigned/Working on it | 03/02 - Monday | 04/02 - Tuesday | 05/02 - Wednesday | 06/02 - Thursday | 07/02 - Friday | 08/02 - Saturday
Sprint 2 | A patient should be able to view institutions on map | 8 | 6 | Completed ¦¦ 03/02 - 04/02 |  | 3=1+1+1 | 3=1+1+1 |  |  |  |  | Easily implemented once the api functions were figured out
| A patient should be able to find institution based on distance Or Price | 8 | 4 | Completed ¦¦ 03/02 - 05/02 |  | 2=1+1 | 1=1 | 1=1 |  |  |  | Implemented the price easily however distance was difficult due to testing, found a way using chrome
| A Patient should be able to find institutes showing price and distance | 8 | 4 | Completed ¦¦ 05/02 - 06/02 |  |  |  | 2=1+1 | 2=1+1 |  |  | After finding a way to test it, it was easy to implement due to research done
| A patient should be able to find institution by price based on procedures | 8 | 4 | Completed ¦¦ 04/02 - 06/02 |  |  | 2=1+1 | 1=1 | 1=1 |  |  | It was done after discussion on how to do it with the group, we all came to a conclusion
| A patient should be able to view institutions on map as well as price | 7 | 4 | Completed ¦¦ 06/02 - 07/02 |  |  |  |  | 2=1+1 | 2=1+1 |  | Prices are on the map markers, just need to click it
| A patient can track current location on map | 7 | 4 | Completed ¦¦ 03/02 - 04/02 |  | 2=1+1 | 2=1+1 |  |  |  |  | Due to research of the map api, this was easy to implement, No problems were encountered
| A patient can input own location on map | 7 | 4 | Completed ¦¦ 05/02 - 06/02 |  |  |  | 2=1+1 | 2=1+1 |  |  | Users geo location is set automatically but can change it if they wish
| A Patient should be able to view his location on the map | 7 | 4 | Completed ¦¦ 04/02 - 05/02 |  |  | 2=1+1 | 2=1+1 |  |  |  | A different marker is present for the user location
| A Patient should be able to insert part of a procedure name in order to retrieve full procedure name | 7 | 3 | Completed ¦¦ 03/02 - 05/02 |  | 2=1+1 |  | 1=1 |  |  |  | The search function implementation was easy due to bootstrap
| A Patient should be able to find institution just based on procedures | 6 | 3 | Completed ¦¦ 05/02 - 07/02 |  |  |  |  | 2=1+1 | 1=1 |  | There was a slight problem but we all grouped up to talk about it and solve it
|  |  |  | Story Points Left | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
[5 empty] | 40 | 31 | 21 | 12 | 3 | 0 | Note: Colour
[5 empty] | 40 | 32 | 24 | 16 | 8 | 0 | Alif
Dillon
Ren
| New points for the sprint backlog founded from sprint 2 for sprint 3: | Reason: | [8 empty] | Costin
| User should be able to differentiate between markers on map | QoL | [8 empty] | Jay
| User should be able to get an update on the table when distance radius is lowered | Userbility and making sure that the user is getting correct info | [8 empty] | Justus
| User should be able to change distance radius when map is displayed | From sprint Review