## Sheet1
| Backlog | Status |  |  |  | Week 1(27/01/2020 - 31/01/2020) | [5 empty] | Comments
| Product | Priority[P] | Estimate[E] | Completed/Incompleted ¦¦ Sart:End | Assigned/Working on it | 27/01 - Monday | 28/01 - Tuesday | 29/01 - Wednesday | 30/01 - Thursday | 31/01 - Friday | 01/02 - Saturday
Sprint 1 | Research Unit testing for PHP and how to implement | 10 | 6 | Completed ¦¦ 27/01 - 29/01 | Jay | 3 | 2 | 1 |  |  |  | It was hard to accomplish however i have a good grasp on it
| Research Map API to use and how to implement | 10 | 5 | Completed ¦¦ 27/01 - 29/01 | Renata, Dillon | 1 | 2 | 2 |  |  |  | Glad there was plenty of time due to difficulty
| Research how to use Java servelet(Netbeans) | 10 | 5 | Completed ¦¦ 27/01 - 28/01 | Costin | 2 | 3 |  |  |  |  | Decided not to use due to difficulty of implementation and novice skills in group
| Set up Github with html Page View | 10 | 1 | Completed ¦¦ 27/01 - 27/01 | Alif | 1 | [5 empty] | It was quick and not much however adding collaboraters and retrieving usernames
| Research geocoding and how to utilise with API | 10 | 6 | Completed ¦¦ 29/01 - 30/01 | Renata, Dillon |  |  | 3 | 3 |  |  | Took longer than expected to develop solution to receiving geolocation
| Research transfer of excel data into MYSQL workbench (database) and transfer it | 10 | 2 | Completed ¦¦ 28/01 - 29/01 | Alif |  | 1 | 1 |  |  |  | I was looking in the wrong area however it was quick and easy to after realisation
| Create/choose HTML backbone for project | 9 | 1 | Completed ¦¦ 27/01 - 27/01 | Alif | 1 | [5 empty] | I just chose the simplest one on bootstrap it can be changed in the future if need be
| Secure a database and webspace(for hosting) for this project | 9 | 1 | Completed ¦¦ 28/01 - 28/01 | Alif |  | 1 |  |  |  |  | This took longer than intended due to inexperience and needed info from tech
| Translate unique location in data set into geolocation(x & y) | 8 | 1 | Completed ¦¦ 29/01 - 29/01 | Alif |  |  | 1 |  |  |  | Methodology was given by ren and dillon so it was simple after database querys just time
| A patient should be able to list institues showing price | 8 | 3 | Completed ¦¦ 28/01 - 30/01 | Alif, Costin, Jay |  | 1 | 1 | 1 |  |  | It just took time as we were all comfortable with php and mysql
| A patient should be able to list institutions sorted by price of procedure | 8 | 3 | Completed ¦¦ 29/01 - 30/01 | Alif, Costin, Jay |  |  | 2 | 1 |  |  | It went well without a hitch
| A patient should be able to retrieve institutions address and zipcode | 8 | 3 | Completed ¦¦ 29/01 - 30/01 | Alif, Costin, jay |  |  | 1 | 2 |  |  | We were also trying to implement Ajax however decided to focus that on sprint 2
| A patient should be able to view map | 8 | 1 | Completed ¦¦ 30/01 - 31/01 | Renata, Dillon, Alif, Costin, Jay |  |  |  | 1 |  |  | A slight setback with the maps however it was solved for now
| A patient should be able to select what procedure they want for institution list | 8 | 3 | Completed ¦¦ 29/01 - 30/01 | Alif, Costin, Jay |  |  | 1 | 2 |  |  | Done Without setbacks
|  |  |  | Story Points Left | Day 0 | Day 1 | Day 2 | Day 3 | Day 4
[5 empty] | 41 | 33 | 23 | 10 | 0
[5 empty] | 41 | 30.75 | 20.5 | 10.25 | 0
| New points for the sprint backlog founded from sprint 1 for sprint 2: | Reason:
| A patient should get a list of institutes from just procedures E:4 P:6 | QoL and ease of usage
| Research new API for maps E:2 P:6 | Old API usage needed server to run however unsure
| Make sure that the elements on website changes with device E:1 P:2 | (QoL)Phones and laptops work however font is too big
Note:
Unit of Work is determined by work done in comparison to the product backlog. So if an individual/ group
does 3 story points and the estimate is 5, then there is an estimate of 2 story points left to do. It is the amount of work done
In comparison to the estimate. Story points done in a group(e.g Jay, Costin, Alif) are story points done by everyone, everyone
spent the same amount of hours completing that amount of work becauase they were physically there and left together afterwords.