## Sheet1
What went well in the Sprint | What could be improved | What will we commit to improve in the next Sprint
We managed to get our sprint 1 story points done on time | We could improve the Priority and Estimate estimation for our sprint backlog | We will commit to improving our sprint backlog with the review we have been given
We worked nicely as a team using pair proggraming where appropriate | We could communicate better in between our groups for example need of a server for the maps | We will commit to making sure that each of our branches are up to date with master
We work well in our individual groups | We could improve keeping other branches up to date with master | We will commit to making sure that master is the most updated branch
| We could improve keeping our master branch the most up to date branch | We will make sure to communicate even when we are working on different matters
We could improve asking for help instead of working through it alone in silence